## Detailed_Data
Release ID | PM ID | Project Area | Root Item Type | Release Status | Release Owner | Release Created | Release Resolved | Category | Hours | Task ID | Type | Department | Task Owner | Country | Title | Task Created | Task Resolved | Month | Year
5576076 |  | CUS Mazda - Production | Review | passed | EXTERNAL Bui Tuan Dung (HCLTech, MS/EHV33-VM) | 29-03-2025 | 02-04-2025 | NET DEV | 1 | 5576076 | review | net | EXTERNAL Bui Tuan Dung (HCLTech, MS/EHV33-VM) | Vietnam | [Review][NET][dSD][EA][Mazda][ESP10][J03MN][BL06-BL08] CAN Update | 29-03-2025 | 02-04-2025 | 4 | 2025
5576075 |  | CUS Mazda - Production | Task | solved | EXTERNAL Bui Tuan Dung (HCLTech, MS/EHV33-VM) | 29-03-2025 | 02-04-2025 | NET DEV | 8 | 5576075 | task | net | EXTERNAL Bui Tuan Dung (HCLTech, MS/EHV33-VM) | Vietnam | [Task][NET][dSD][Mazda][ESP10][J03MN][BL06-BL08] CAN Update | 29-03-2025 | 02-04-2025 | 4 | 2025
5550177 |  | CUS Mazda - Production | Defect | confirmed | Le Thi My Duyen (MS/EHV22-VM) | 24-03-2025 | 26-03-2025 | NET REWORK | 7 | 5550177 | defect | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [DEFECT][Mazda][ESP10][J03MN][BL08] ID415 is stopped and could not be re-started after IG ON | 24-03-2025 | 26-03-2025 | 3 | 2025
5478981 |  | CUS Mazda - Production | Task | solved | Le Thi My Duyen (MS/EHV22-VM) | 03-03-2025 | 14-08-2026 | NET DEV | 62.5 | 5478981 | task | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [Task][MZC][ESP10][J12S][NET] Non-Development Activity | 03-03-2025 | 14-08-2026 | 8 | 2026
5399584 |  | CUS Mazda - Production | Task | solved | Le Thi My Duyen (MS/EHV22-VM) | 10-02-2025 | 14-08-2026 | NET DEV | 16 | 5399584 | task | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [Task][MZC][ESP10][J12S][NET] Non-Development Activity | 10-02-2025 | 14-08-2026 | 8 | 2026
5095983 |  | CUS Mazda - Production | Task | solved | Le Thi My Duyen (MS/EHV22-VM) | 28-10-2024 | 14-08-2026 | NET DEV | 127 | 5095983 | task | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [Task][MZC][ESP10][J03M][NET] Non-Development Activity | 28-10-2024 | 14-08-2026 | 8 | 2026
6139597 | BM-00099111 | CUS Mazda - Production | Release | solved | Nguyen Le Gia Bach (MS/EJH2-VM) | 15-09-2025 | 30-06-2026 | DCOM DEV | 8 | 6217989 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Task][DCOM][Constr][MAZDA][ESP10CB][IPM9_RC][BL12.6.1][SD + dSD + Impl] Update read out data for DID$DD19 | 10-10-2025 | 22-10-2025 | 10 | 2025
6139597 | BM-00099111 | CUS Mazda - Production | Release | solved | Nguyen Le Gia Bach (MS/EJH2-VM) | 15-09-2025 | 30-06-2026 | DCOM DEV | 2 | 6217990 | review | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Review][DCOM][Constr] [MAZDA][ESP10CB][IPM9_RC][BL12.6.1][SD + dSD + Impl] Update read out data for DID$DD19 | 10-10-2025 | 22-10-2025 | 10 | 2025
6139597 | BM-00099111 | CUS Mazda - Production | Release | solved | Nguyen Le Gia Bach (MS/EJH2-VM) | 15-09-2025 | 30-06-2026 | DCOM DEV | 2 | 6217992 | review | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Review][DCOM][Constr] [MAZDA][ESP10CB][IPM9_RC][BL12.6.1][SW CT] Update read out data for DID$DD19 | 10-10-2025 | 22-10-2025 | 10 | 2025
6139597 | BM-00099111 | CUS Mazda - Production | Release | solved | Nguyen Le Gia Bach (MS/EJH2-VM) | 15-09-2025 | 30-06-2026 | DCOM DEV | 2 | 6217991 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Task][DCOM][Constr][MAZDA][ESP10CB][IPM9_RC][BL12.6.1][SW CT] Update read out data for DID$DD19 | 10-10-2025 | 22-10-2025 | 10 | 2025
6139597 | BM-00099111 | CUS Mazda - Production | Release | solved | Nguyen Le Gia Bach (MS/EJH2-VM) | 15-09-2025 | 30-06-2026 | DCOM DEV | 1 | 6262857 | review | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Review][DCOM][ReqEng][MAZDA][ESP10CB][IPM9_RC][BL12.6.1] Update read out data for DID$DD19 | 21-10-2025 | 22-10-2025 | 10 | 2025
6139597 | BM-00099111 | CUS Mazda - Production | Release | solved | Nguyen Le Gia Bach (MS/EJH2-VM) | 15-09-2025 | 30-06-2026 | DCOM DEV | 1 | 6217995 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Task][DCOM][ReqEng][MAZDA][ESP10CB][IPM9_RC][BL12.6.1] Update read out data for DID$DD19 | 10-10-2025 | 22-10-2025 | 10 | 2025
6139597 | BM-00099111 | CUS Mazda - Production | Release | solved | Nguyen Le Gia Bach (MS/EJH2-VM) | 15-09-2025 | 30-06-2026 | NET DEV | 40 | 6358205 | task | var | Nguyen Trong Nhat (MS/EJH21-VM) | India | [MAZDA][ESP10CB][J12S_IPM9][GeneralBaseline][Task][VAR] Variant Coding CFS Verification<br/> | 11-11-2025 | 13-01-2026 | 1 | 2026
6139597 | BM-00099111 | CUS Mazda - Production | Release | solved | Nguyen Le Gia Bach (MS/EJH2-VM) | 15-09-2025 | 30-06-2026 | NET DEV | 0.5 | 6358300 | review | var | Nguyen Trong Nhat (MS/EJH21-VM) | India | [MAZDA][ESP10CB][J12S_IPM9][GeneralBaseline][Review][VAR] Variant Coding CFS Verification | 11-11-2025 | 13-01-2026 | 1 | 2026
6075789 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 26-08-2025 | 25-06-2026 | DCOM DEV | 107.9 | 6277209 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Task][DCOM][MAZDA][ESP10CB][J03M][GeneralBaseline][SW-PCM] CFS Verification &amp; Deliverables | 24-10-2025 | 23-12-2025 | 12 | 2025
5032875 | BM-00092864 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 08-10-2024 | 02-10-2025 | DCOM DEV | 1 | 5279476 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [DCOM][ReqEng][EPIC][MAZDA][ESP10][J12S][BL12_5_2][DCOM] Update scope for IPM9 | 24-12-2024 | 20-08-2025 | 8 | 2025
5032875 | BM-00092864 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 08-10-2024 | 02-10-2025 | DCOM DEV | 1 | 6006155 | review | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Review][DCOM][ReqEng][EPIC][MAZDA][ESP10][J12S][BL12_5_2][DCOM] Update scope for IPM9 | 04-08-2025 | 20-08-2025 | 8 | 2025
5032875 | BM-00092864 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 08-10-2024 | 02-10-2025 | DCOM DEV | 1.5 | 5279471 | review | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Review][DCOM][Constr][EPIC][MAZDA][ESP10][J12S][BL12_5_2][DCOM][SD + dSD + Impl] Update scope for IPM9 | 24-12-2024 | 20-08-2025 | 8 | 2025
5032875 | BM-00092864 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 08-10-2024 | 02-10-2025 | DCOM DEV | 40 | 5279470 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [DCOM][Constr][EPIC][MAZDA][ESP10][J12S][BL12_5_2][DCOM][SD + dSD + Impl] Update scope for IPM9 | 24-12-2024 | 20-08-2025 | 8 | 2025
5032875 | BM-00092864 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 08-10-2024 | 02-10-2025 | DCOM DEV | 1.5 | 5279473 | review | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Review][DCOM][Constr][EPIC][MAZDA][ESP10][J12S][BL12_5_2][DCOM][SW CT] Update scope for IPM9 | 24-12-2024 | 20-08-2025 | 8 | 2025
5032875 | BM-00092864 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 08-10-2024 | 02-10-2025 | DCOM DEV | 16 | 5279472 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [DCOM][Constr][EPIC][MAZDA][ESP10][J12S][BL12_5_2][DCOM][SW CT] Update scope for IPM9 | 24-12-2024 | 20-08-2025 | 8 | 2025
5032875 | BM-00092864 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 08-10-2024 | 02-10-2025 | NET DEV | 8 | 6045984 | task | var | EXTERNAL Nguyen Hoang Nhat Long (FPT Software, MS/EAS5-VM) | India | [TASK][MAZDA][ESP10][J12S][BL12_5_3][VAR] CFS preparation | 15-08-2025 | 19-08-2025 | 8 | 2025
5032875 | BM-00092864 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 08-10-2024 | 02-10-2025 | NET DEV | 8 | 6046078 | review | var | EXTERNAL Nguyen Hoang Nhat Long (FPT Software, MS/EAS5-VM) | India | [REVIEW][MAZDA][ESP10][J12S][BL12_5_3][VAR] CFS preparation | 15-08-2025 | 19-08-2025 | 8 | 2025
5032875 | BM-00092864 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 08-10-2024 | 02-10-2025 | NET DEV | 52 | 5657949 | task | var | EXTERNAL Nguyen Hoang Nhat Long (FPT Software, MS/EAS5-VM) | India | [TASK][MAZDA][ESP10][J12S][BL12_5_3][VAR] GCC learning logic addition | 22-04-2025 | 03-09-2025 | 9 | 2025
5032875 | BM-00092864 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 08-10-2024 | 02-10-2025 | NET DEV | 8 | 6045596 | review | var | EXTERNAL Nguyen Hoang Nhat Long (FPT Software, MS/EAS5-VM) | India | [REVIEW][MAZDA][ESP10][J12S][BL12_5_3][VAR] GCC learning logic addition | 15-08-2025 | 03-09-2025 | 9 | 2025
5032875 | BM-00092864 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 08-10-2024 | 02-10-2025 | DCOM DEV | 1 | 5973966 | review | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Review][MZC][J12S][DCOM][CFS] CAN Diagnosis Functional Description | 24-07-2025 | 30-07-2025 | 7 | 2025
5032875 | BM-00092864 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 08-10-2024 | 02-10-2025 | DCOM DEV | 1 | 5973959 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Task][MZC][J12S][DCOM][CFS] CAN Diagnosis Functional Description | 24-07-2025 | 30-07-2025 | 7 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 40 | 5052379 | task | var | EXTERNAL Nguyen Hoang Nhat Long (FPT Software, MS/EAS5-VM) | India | [MAZDA][ESP10][J03M][BL09][Task][VAR] CFS preparation | 14-10-2024 | 04-08-2025 | 8 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 8 | 5815246 | review | var | EXTERNAL Nguyen Hoang Nhat Long (FPT Software, MS/EAS5-VM) | India | [MAZDA][ESP10][J03M][BL09][Review][VAR] CFS preparation | 12-06-2025 | 04-08-2025 | 8 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 40 | 5742386 | task | var | EXTERNAL Nguyen Hoang Nhat Long (FPT Software, MS/EAS5-VM) | India | [MAZDA][ESP10][J03M][BL09][Task][VAR] Remove additional variant for Vehicle Test | 20-05-2025 | 04-08-2025 | 8 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 8 | 5908189 | review | var | EXTERNAL Nguyen Hoang Nhat Long (FPT Software, MS/EAS5-VM) | India | [MAZDA][ESP10][J03M][BL09][Review][VAR] Remove additional variant for Vehicle Test | 07-07-2025 | 04-08-2025 | 8 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 0.5 | 5653704 | review | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [Review][MAZDA][ESP10][J03M][BL09][NET][SW CT] EDR Development and PrkBrkActv_D_Actl | 21-04-2025 | 30-05-2025 | 5 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 16.5 | 5653703 | task | net | EXTERNAL Bui Tuan Dung (HCLTech, MS/EHV33-VM) | Vietnam | [TASK][MAZDA][ESP10][J03M][BL09][NET][SW CT] EDR Development and PrkBrkActv_D_Actl | 21-04-2025 | 30-05-2025 | 5 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 10 | 5653698 | task | net | EXTERNAL Bui Tuan Dung (HCLTech, MS/EHV33-VM) | Vietnam | [TASK][MAZDA][ESP10][J03M][BL09][NET][SW UT] EDR Development and PrkBrkActv_D_Actl | 21-04-2025 | 30-05-2025 | 5 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 51.5 | 5653693 | task | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [TASK][MAZDA][ESP10][J03M][BL09][NET][Impl.] EDR Development and PrkBrkActv_D_Actl | 21-04-2025 | 30-05-2025 | 5 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 2.5 | 5653696 | review | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [Review][MAZDA][ESP10][J03M][BL09][NET][Impl.] EDR Development and PrkBrkActv_D_Actl | 21-04-2025 | 30-05-2025 | 5 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 0.5 | 5653701 | review | net | EXTERNAL Bui Tuan Dung (HCLTech, MS/EHV33-VM) | Vietnam | [Review][MAZDA][ESP10][J03M][BL09][NET][SW UT] EDR Development and PrkBrkActv_D_Actl | 21-04-2025 | 30-05-2025 | 5 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 28 | 5473713 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [DCOM][Constr][MAZDA][ESP10][J03M][BL09][Task][SW CT] EDR Development | 28-02-2025 | 10-07-2025 | 7 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 20.5 | 5473714 | review | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Review][DCOM][Constr][MAZDA][ESP10][J03M][BL09][SW CT] EDR Development | 28-02-2025 | 10-07-2025 | 7 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 36 | 5473712 | review | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Review][DCOM][Constr][MAZDA][ESP10][J03M][BL09][SD + dSD + Impl] EDR Development | 28-02-2025 | 10-07-2025 | 7 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 180 | 5473711 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [DCOM][Constr][MAZDA][ESP10][J03M][BL09][Task][SD + dSD + Impl] EDR Development | 28-02-2025 | 10-07-2025 | 7 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 16 | 5674127 | review | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Review][DCOM][ReqEng][MAZDA][ESP10][J03M][BL09][Epic][DCOM] EDR Development | 28-04-2025 | 10-07-2025 | 7 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 116 | 5473717 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [DCOM][ReqEng][MAZDA][ESP10][J03M][BL09][Epic][DCOM] EDR Development | 28-02-2025 | 10-07-2025 | 7 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 0.5 | 5318072 | task | var | Huynh Khanh Khoi Nguyen (MS/EAA1-VM) | India | [TASK][MAZDA][ESP10][J03M][BL07][VAR]Update SCBS2, VarUnsupportedFactoryOption FW | 10-01-2025 | 17-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 0.5 | 5647607 | review | var | EXTERNAL Nguyen Hoang Nhat Long (FPT Software, MS/EAS5-VM) | India | [REVIEW][MAZDA][ESP10][J03M][BL07][VAR]Update SCBS2, VarUnsupportedFactoryOption FW | 17-04-2025 | 17-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 101.5 | 5278516 | task | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [TASK][NET][MAZDA][ESP10][J03M][BL07[Impl.] Update ADAS Monitoring &amp; AVH performance update from JT | 23-12-2024 | 05-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 0.5 | 5278519 | review | net | EXTERNAL Bui Tuan Dung (HCLTech, MS/EHV33-VM) | Vietnam | [Review][NET][Impl.][MAZDA][ESP10][J03M][BL07[Epic][LDM][SW UT] Update ADAS Monitoring &amp; AVH performance update from JT | 23-12-2024 | 28-02-2025 | 2 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 4 | 5278517 | review | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [Review][NET][MAZDA][ESP10][J03M][BL07][Impl.] Update ADAS Monitoring &amp; AVH performance update from JT | 23-12-2024 | 05-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 5 | 5278518 | task | net | EXTERNAL Bui Tuan Dung (HCLTech, MS/EHV33-VM) | Vietnam | [TASK][MAZDA][ESP10][J03M][BL07][SW UT] Update ADAS Monitoring &amp; AVH performance update from JT | 23-12-2024 | 05-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 6 | 5278521 | review | net | EXTERNAL Bui Tuan Dung (HCLTech, MS/EHV33-VM) | Vietnam | [Review][NET][MAZDA][ESP10][J03M][BL07][SW CT] Update ADAS Monitoring &amp; AVH performance update from JT | 23-12-2024 | 05-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 25 | 5278520 | task | net | EXTERNAL Bui Tuan Dung (HCLTech, MS/EHV33-VM) | Vietnam | [TASK][MAZDA][ESP10][J03M][BL07][SW CT] Update ADAS Monitoring &amp; AVH performance update from JT | 23-12-2024 | 05-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 1.5 | 5464048 | review | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [REVIEW][[MAZDA][ESP10][J03M][BL08][LDM request] NET:MRCC development NET failure signal updated | 26-02-2025 | 03-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 7.5 | 5464034 | task | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [TASK][[MAZDA][ESP10][J03M][BL08][LDM request] NET:MRCC development NET failure signal updated | 26-02-2025 | 03-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 20 | 5288212 | review | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Review][DCOM][Constr][EPIC][Mazda][ESP10][J03M][BL07][SW CT] Logic Improvement and Finalize Document | 31-12-2024 | 14-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 60 | 5288211 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [DCOM][Constr][EPIC][Mazda][ESP10][J03M][BL07][SW CT] Logic Improvement and Finalize Document | 31-12-2024 | 14-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 120 | 5288209 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [DCOM][Constr][EPIC][Mazda][ESP10][J03M][BL07][SD + dSD + Impl] Logic Improvement and Finalize Document | 31-12-2024 | 14-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 22.5 | 5288210 | review | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Review][DCOM][Constr][EPIC][Mazda][ESP10][J03M][BL07][SD + dSD + Impl] Logic Improvement and Finalize Document | 31-12-2024 | 14-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 2 | 5623005 | review | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Review][DCOM][ReqEng][EPIC][Mazda][ESP10][J03M][BL07] Logic Improvement and Finalize Document | 10-04-2025 | 14-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 16 | 5288215 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [DCOM][ReqEng][EPIC][Mazda][ESP10][J03M][BL07] Logic Improvement and Finalize Document | 31-12-2024 | 14-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 128 | 5192451 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [DCOM][Constr][EPIC][MAZDA][ESP10][J03M][BL05][DCOM][SD + dSD + Impl] Update SID0x14 and Defect Fix | 25-11-2024 | 09-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 32 | 5192453 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [DCOM][Constr][EPIC][MAZDA][ESP10][J03M][BL05][DCOM][SW CT] Update SID0x14 and Defect Fix | 25-11-2024 | 09-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 20.5 | 5192452 | review | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Review][DCOM][Constr][EPIC][MAZDA][ESP10][J03M][BL05][DCOM][SD + dSD + Impl] Update SID0x14 and Defect Fix | 25-11-2024 | 09-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 20.5 | 5192454 | review | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Review][DCOM][Constr][EPIC][MAZDA][ESP10][J03M][BL05][DCOM][SW CT] Update SID0x14 and Defect Fix | 25-11-2024 | 09-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 32 | 5192457 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [DCOM][ReqEng][EPIC][MAZDA][ESP10][J03M][BL05][DCOM] Update SID0x14 and Defect Fix | 25-11-2024 | 09-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 8 | 5614509 | review | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Review][DCOM][ReqEng][EPIC][MAZDA][ESP10][J03M][BL05][DCOM] Update SID0x14 and Defect Fix | 08-04-2025 | 09-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 139 | 4541439 | task | var | Huynh Khanh Khoi Nguyen (MS/EAA1-VM) | India | [Mazda][ESP10][J03MN][BL04] VAR Migration and Adaptation | 07-05-2024 | 02-05-2025 | 5 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 20 | 5648974 | review | var | Huynh Khanh Khoi Nguyen (MS/EAA1-VM) | India | [Mazda][ESP10][J03MN][BL04][Review] VAR Migration and Adaptation | 17-04-2025 | 02-05-2025 | 5 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 0.1 | 4650217 | task | var | Huynh Khanh Khoi Nguyen (MS/EAA1-VM) | India | [Mazda][ESP10][J03MN][ADAS] Variant Implementation Contributes To Functional Requirements | 07-06-2024 | 02-05-2025 | 5 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM REWORK | 0.5 | 6011147 | review | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Review][DCOM][Constr] Fix for Defect: [DEFECT][Mazda][ESP10][J03M][BL09.2][SD + dSD + Impl] Redundant NVM of &quot;EEPlantSafeKeyNumber&quot; | 05-08-2025 | 06-08-2025 | 8 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM REWORK | 4 | 6011146 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [DCOM][Constr] Fix for Defect: [DEFECT][Mazda][ESP10][J03M][BL09.2][SD + dSD + Impl] Redundant NVM of &quot;EEPlantSafeKeyNumber&quot; | 05-08-2025 | 06-08-2025 | 8 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 116 | 5884792 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Mazda][DCOM] Non-development activities | 01-07-2025 | 31-10-2025 | 10 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 20 | 5577779 | task | var | EXTERNAL Nguyen Hoang Nhat Long (FPT Software, MS/EAS5-VM) | India | [MAZDA][ESP10][J03M][BL08][Task][VAR] CDP update | 31-03-2025 | 02-05-2025 | 5 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 0.5 | 5647874 | review | var | EXTERNAL Nguyen Hoang Nhat Long (FPT Software, MS/EAS5-VM) | India | [MAZDA][ESP10][J03M][BL08][Review][VAR] CDP update | 17-04-2025 | 17-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET REWORK | 1 | 5987931 | task | net | EXTERNAL Bui Tuan Dung (HCLTech, MS/EHV33-VM) | Vietnam | [TASK][NET][Impl.] Fix for Defect: [DEFECT][Mazda][ESP10][J03M][BL09.2][SW UT] CAN signal of BpedMove_D_Actl doesnt relfect actual state | 29-07-2025 | 04-08-2025 | 8 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET REWORK | 2 | 5987933 | task | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [TASK][NET][Impl.] Fix for Defect: [DEFECT][Mazda][ESP10][J03M][BL09.2][SW CT] CAN signal of BpedMove_D_Actl doesnt relfect actual state | 29-07-2025 | 04-08-2025 | 8 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET REWORK | 1 | 5987930 | review | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [Review][NET][Impl.] Fix for Defect: [DEFECT][Mazda][ESP10][J03M][BL09.2][Impl.] CAN signal of BpedMove_D_Actl doesnt relfect actual state | 29-07-2025 | 04-08-2025 | 8 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET REWORK | 0.1 | 5987932 | review | net | EXTERNAL Bui Tuan Dung (HCLTech, MS/EHV33-VM) | Vietnam | [Review][NET][Impl.] Fix for Defect: [DEFECT][Mazda][ESP10][J03M][BL09.2][SW UT] CAN signal of BpedMove_D_Actl doesnt relfect actual state | 29-07-2025 | 04-08-2025 | 8 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET REWORK | 0.5 | 5987934 | review | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [Review][NET][Impl.] Fix for Defect: [DEFECT][Mazda][ESP10][J03M][BL09.2][SW CT] CAN signal of BpedMove_D_Actl doesnt relfect actual state | 29-07-2025 | 04-08-2025 | 8 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET REWORK | 28 | 5987929 | task | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [TASK][NET][Impl.] Fix for Defect: [DEFECT][Mazda][ESP10][J03M][BL09.2][Impl.] CAN signal of BpedMove_D_Actl doesnt relfect actual state | 29-07-2025 | 04-08-2025 | 8 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 1 | 5808709 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Task][MZC][J03M][DCOM][SSDS] Subsystem Specific Diagnostic Specification | 10-06-2025 | 31-10-2025 | 10 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 1 | 5808634 | review | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Review][MZC][J03M][DCOM][CFS] CAN Diagnosis Functional Description | 10-06-2025 | 02-10-2025 | 10 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 2 | 5808718 | review | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Review][MZC][J03M][DCOM][SSDS] Subsystem Specific Diagnostic Specification | 10-06-2025 | 02-10-2025 | 10 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | DCOM DEV | 1 | 5808625 | task | dcom | Trinh Gia Bao (MS/EHV32-VM) | Vietnam | [Task][MZC][J03M][DCOM][CFS] CAN Diagnosis Functional Description | 10-06-2025 | 02-10-2025 | 10 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 4 | 5426830 | task | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [TASK][MAZDA][ESP10][J03M][BL08][NET][SW CT] NET fix for missing update | 17-02-2025 | 03-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 8 | 5426828 | task | net | EXTERNAL Bui Tuan Dung (HCLTech, MS/EHV33-VM) | Vietnam | [TASK][NET][Impl.][MAZDA][ESP10][J03M][BL08][Epic][NET][SW UT] NET fix for missing update | 17-02-2025 | 03-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 55 | 5426826 | task | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [TASK][MAZDA][ESP10][J03M][BL08][NET][Impl.] NET fix for missing update | 17-02-2025 | 03-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 1 | 5426829 | review | net | EXTERNAL Bui Tuan Dung (HCLTech, MS/EHV33-VM) | Vietnam | [Review][NET][Impl.][MAZDA][ESP10][J03M][BL08][Epic][NET][SW UT] NET fix for missing update | 17-02-2025 | 31-03-2025 | 3 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 6 | 5426827 | review | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [Review][MAZDA][ESP10][J03M][BL08][NET][Impl.] NET fix for missing update | 17-02-2025 | 03-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 5.5 | 5426831 | review | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [Review][MAZDA][ESP10][J03M][BL08][NET][SW CT] NET fix for missing update | 17-02-2025 | 03-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 40 | 5237070 | task | var | Huynh Khanh Khoi Nguyen (MS/EAA1-VM) | India | [MAZDA][ESP10][J03M][BL06][Task][VAR] Add additional variant for Vehicle Test | 09-12-2024 | 30-07-2025 | 7 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 2 | 5909418 | review | var | EXTERNAL Nguyen Hoang Nhat Long (FPT Software, MS/EAS5-VM) | India | [MAZDA][ESP10][J03M][BL06][Review][VAR] Add additional variant for Vehicle Test | 07-07-2025 | 30-07-2025 | 7 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 21 | 5239738 | task | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [TASK][MAZDA][ESP10][J03M][BL06][NET] Add additional variant for Vehicle Test | 10-12-2024 | 02-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET DEV | 2.5 | 5566640 | review | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [REVIEW][MAZDA][ESP10][J03M][BL06][NET] Add additional variant for Vehicle Test | 27-03-2025 | 02-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET REWORK | 1 | 5475558 | review | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [REVIEW][Mazda][ESP10][J03MN][BL08] HlaCtl_D_Actl, SlaCtl_D_Actl signals in CAN are set as &quot;Not Confiugred&quot; | 01-03-2025 | 03-04-2025 | 4 | 2025
4217956 | BM-00092843 | CUS Mazda - Production | Release | solved | Nguyen Chau Long (MS/EJH2-VM) | 18-01-2024 | 31-10-2025 | NET REWORK | 6 | 5475557 | task | net | Le Thi My Duyen (MS/EHV22-VM) | Vietnam | [TASK][Mazda][ESP10][J03MN][BL08] HlaCtl_D_Actl, SlaCtl_D_Actl signals in CAN are set as &quot;Not Confiugred&quot; | 01-03-2025 | 03-04-2025 | 4 | 2025

## Vietnam
Scenario | Release ID Status / Explanation | Effort in hrs | Description
Closed Release IDs only | Closed | 0 | Country='Vietnam', Year=2026, Month in 1-6, Category in ['DCOM DEV', 'NET DEV', 'DCOM REWORK', 'NET REWORK', 'DSM DEV', 'DSM REWORK'], Root Item Type='Release', Release Status in ['solved']
All relevant Release IDs | New + In Progress (Release Ids) | 0 | Country='Vietnam', Year=2026, Month in 1-6, Category in ['DCOM DEV', 'NET DEV', 'DCOM REWORK', 'NET REWORK', 'DSM DEV', 'DSM REWORK'], Root Item Type='Release', Release Status in ['unresolved (new / in progress)']
Linked to release ID | New + In Progress (Task Ids) | 0 | Country='Vietnam', Year=2027, Root Item Type='Release', Creation Date in 2026 (Jan-Jun)
Linked to release ID- & Not linked to release ID | WIs are not mapped to the correct filed against | 0 | Country='Vietnam', Year=2026, Month in 1-6, Category='GENERAL Miscategorized'
Not linked to release ID | Defect | 0 | (Country='Vietnam', Year=2026, Month 1-6, Root Item='Defect', Category != 'GENERAL Miscategorized') + (Country='Vietnam', Year=2027, Root Item='Defect')
Not linked to release ID | Orphan | 0 | (Country='Vietnam', Year=2026, Month 1-6, Root Item in ['Defectfix', 'Task', 'Review', 'Epic', 'Story'], Category != 'GENERAL Miscategorized') + (Country='Vietnam', Year=2027, Root Item in ['Defectfix', 'Task', 'Review', 'Epic', 'Story'])

## India
Scenario | Release ID Status / Explanation | Effort in hrs | Description
Closed Release IDs only | Closed | 40 | Country='India', Year=2026, Month in 1-6, Category in ['DCOM DEV', 'NET DEV', 'DCOM REWORK', 'NET REWORK', 'DSM DEV', 'DSM REWORK'], Root Item Type='Release', Release Status in ['solved']
All relevant Release IDs | New + In Progress (Release Ids) | 0 | Country='India', Year=2026, Month in 1-6, Category in ['DCOM DEV', 'NET DEV', 'DCOM REWORK', 'NET REWORK', 'DSM DEV', 'DSM REWORK'], Root Item Type='Release', Release Status in ['unresolved (new / in progress)']
Linked to release ID | New + In Progress (Task Ids) | 0 | Country='India', Year=2027, Root Item Type='Release', Creation Date in 2026 (Jan-Jun)
Linked to release ID- & Not linked to release ID | WIs are not mapped to the correct filed against | 0 | Country='India', Year=2026, Month in 1-6, Category='GENERAL Miscategorized'
Not linked to release ID | Defect | 0 | (Country='India', Year=2026, Month 1-6, Root Item='Defect', Category != 'GENERAL Miscategorized') + (Country='India', Year=2027, Root Item='Defect')
Not linked to release ID | Orphan | 0 | (Country='India', Year=2026, Month 1-6, Root Item in ['Defectfix', 'Task', 'Review', 'Epic', 'Story'], Category != 'GENERAL Miscategorized') + (Country='India', Year=2027, Root Item in ['Defectfix', 'Task', 'Review', 'Epic', 'Story'])

## WW
Scenario | Release ID Status / Explanation | Effort in hrs | Description
Closed Release IDs only | Closed | 40 | Country=WW (All Countries), Year=2026, Month in 1-6, Category in ['DCOM DEV', 'NET DEV', 'DCOM REWORK', 'NET REWORK', 'DSM DEV', 'DSM REWORK'], Root Item Type='Release', Release Status in ['solved']
All relevant Release IDs | New + In Progress (Release Ids) | 0 | Country=WW (All Countries), Year=2026, Month in 1-6, Category in ['DCOM DEV', 'NET DEV', 'DCOM REWORK', 'NET REWORK', 'DSM DEV', 'DSM REWORK'], Root Item Type='Release', Release Status in ['unresolved (new / in progress)']
Linked to release ID | New + In Progress (Task Ids) | 0 | Country=WW (All Countries), Year=2027, Root Item Type='Release', Creation Date in 2026 (Jan-Jun)
Linked to release ID- & Not linked to release ID | WIs are not mapped to the correct filed against | 0 | Country=WW (All Countries), Year=2026, Month in 1-6, Category='GENERAL Miscategorized'
Not linked to release ID | Defect | 0 | (Country=WW (All Countries), Year=2026, Month 1-6, Root Item='Defect', Category != 'GENERAL Miscategorized') + (Country=WW (All Countries), Year=2027, Root Item='Defect')
Not linked to release ID | Orphan | 0 | (Country=WW (All Countries), Year=2026, Month 1-6, Root Item in ['Defectfix', 'Task', 'Review', 'Epic', 'Story'], Category != 'GENERAL Miscategorized') + (Country=WW (All Countries), Year=2027, Root Item in ['Defectfix', 'Task', 'Review', 'Epic', 'Story'])

## WW_Table
Metric | Vietnam | India | Total
Total Effort (hrs) | 0 | 40 | 40